PROJECT CHARTER

Mechatronics Final-Year Research, Design & Make Project

| Team Number: | 10 |
| --- | --- |
| Project Title: | Design and Development of an Intelligent Hybrid Solar–Biogas Energy Management, Automated Tobacco Handling and Environmental Control System for Sustainable Tobacco Curing |
| Supervisor: | E. Sibanda |
| Team Members: | Lynos T Pasi C22149444V Takudzwa Madoda C22149974V Brighton Njeke C22149686P Wayne Mukucha C22150905H Thabani J. Chasokela C22149549I Kelvin T. Makacha C22150379H Tashinga E Matarirano C22152273O Takura Mupxetedzi C22148980W Justice Tayengwa C22151588P Precious S. Marozva C22149792E |
| Date Submitted: |  |

# 1. Problem Statement

Tobacco curing in Zimbabwe continues to rely heavily on conventional wood-fired curing systems and manual monitoring of temperature and humidity. This dependence on firewood contributes to pressure on forest resources, while manual monitoring can result in inconsistent curing conditions, increased labour requirements and reduced control over the curing process. There is therefore a need for more sustainable and intelligent curing technologies that can improve energy efficiency, environmental sustainability and process control. This project proposes the design and development of an intelligent hybrid tobacco curing barn that combines solar energy and biogas as alternative heat-energy sources, together with automated monitoring and control of key curing parameters. The proposed system supports Zimbabwe’s National Development Strategy 2 (NDS2) priorities on climate-proof agriculture, innovation, sustainable production, value addition and the modernisation of agricultural processes.

# 2. Objectives

1. To design and construct a functional prototype of the hybrid solar-biogas system capable of supplying the required thermal energy for the major stages of tobacco curing by switching between or combining solar and biogas based on energy demand.

2.  To design, fabricate and integrate an automated loading and unloading mechanism with the capability of transferring loaded tobacco racks into and out of the curing chamber with minimal human intervention.

3. To develop and implement an IoT-based automated environment control system to provide real-time monitoring and regulation of key parameters, including temperature and humidity, and also provide the farmer with information on the current curing stage and alert if there are any abnormalities in the operating conditions.

# 3. Scope

In scope:

- Design, construction and testing of a lab-scale model.

- Solar sub-system and biogas sub-system integration.

- Basic instrumentation for temperature and, if feasible, humidity monitoring.

Out of scope:

- Construction of a full-scale, farm-ready barn.

- Detailed anaerobic digester design.

- Commercial costing / manufacturing for sale.

# 4. Success Criteria

- Curing Temperature Control: The prototype shall achieve and maintain the required temperature ranges for the yellowing (35–38°C), colour fixing (38–50°C), and stem drying (50–70°C) stages for the defined test duration.

- Hybrid Energy Performance: The system shall demonstrate that solar and biogas energy sources can individually and jointly provide heat to the curing chamber, with the active energy source and corresponding temperature contribution recorded during testing.

- Moisture Recovery and Productive Use: The system shall successfully capture measurable moisture/condensate produced during curing and demonstrate its suitability for at least one productive agricultural or energy-related application.

- Project Documentation and Traceability: 100% of required planning, design, construction, programming, testing and evaluation documents shall be completed, properly organised and traceable to the project requirements and test results.

- Schedule and Budget Compliance:  The project shall be completed within the approved project schedule and allocated budget, with any deviations documented and justified.

# 5. Milestones & Deliverables

| Milestone | Deliverable | Target Date | Owner |
| --- | --- | --- | --- |
| Proposal Review | Proposal document + panel review | 30/09/26 | Takudzwa Madoda |
| Design Review | CAD, circuit design, control architecture | 30/11/26 | Everyone |
| Preliminary Demo | Bench-level subsystem demo | 26/02/27 | Tashinga E Matarirano |
| Integration Check | Mechanical + electrical + software integrated | 05/03/27 | Wayne Mukucha Thabani J. Chasokela |
| Final Demo | Working prototype + report + poster | 30/04/27 | Lynos T Pasi Takura Mupxetedzi |

# 6. Preliminary Bill of Materials (BOM)

| Item | Qty | Estimated Cost ($) |
| --- | --- | --- |
| DC Heater | 4 | 40 |
| Gas Heater | 2 | 30 |
| Microcontrollers (Arduino + ESP32) | 1 | 20 |
| Battery 12V | 1 | 40 |
| Gas tank | 1 | 20 |
| MPPT Charge Controller 12V | 1 | 30 |
| Solar Panels | 1 | 75 |
| Cables |  | 20 |
| Gas flow sensor | 1 | 5 |
| Gas leakage Sensor | 1 | 4 |
| Gas Igniter | 2 | 10 |
| Solenoid gas valve | 1 | 16 |
| breadboard | 1 | 5 |
| Exhaust fan | 1 | 20 |
| Small wheels | 4 | 4 |
| Perforated trays | 4 | 20 |
| DHT22 Temperature and Humidity Sensor | 2 | 5 |
| Display LCD | 1 | 10 |
| Motors | 2 | 20 |
| Motor driver (A4988) | 2 | 8 |
| Door hinges | 2 | 4 |
| Angle Iron | 6m | 20 |
| Miscellaneous Cost |  | 50 |
| Total |  | 476 |

# 7. Risk Assessment

| Risk | Likelihood (scale 1–5) | Impact | Mitigation Plan |
| --- | --- | --- | --- |
| Electrical short circuit or component failure | 5 | Damage to appliances, controllers, sensors or power electronics; possible overheating or fire. | Use correctly rated cables, fuses/MCBs and protective devices. Separate power and signal wiring, properly terminate connections, and perform continuity and insulation tests before energising the system |
| Limited availability or increasing cost of components | 3 | Delays in procurement may affect the project schedule and budget. | Identify components early, maintain alternative component specifications and prioritise locally available equivalents where possible. |
| Inadequate power to supply the barn | 1 | Failure to adequately cure the tobacco | Having an alternative AC power supply to supplement an alternative design. |

# 8. Interface Contracts (Mechanical / Electrical / Software)

1. Electrical Interfaces

- Power Distribution & Voltage Levels:

  - Low-Voltage Control & Sensing: 5V DC and 3.3V DC supplied via microcontrollers (Arduino & ESP32) and voltage regulators for sensors (DHT22, gas sensors) and the LCD display.

  - Actuation & Power Level: 12V DC bus powered by the 12V battery and MPPT charge controller to drive DC heaters, exhaust fans, solenoid gas valves, and motors.

- Wiring & Protection: Separate routing for high-current power lines (heaters, motors) and low-current signal lines (sensors) minimises electromagnetic interference (EMI). Fuses and relays used for switching high-draw components.

2. Mechanical Interfaces

- Mounting & Enclosures:

  - Control enclosure (housing the Arduino, ESP32, and relay modules) securely mounted to the exterior wall of the curing chamber to protect electronics from high humidity and heat.

  - Actuator and motor mountings aligned with the automated tray/rack loading mechanism using rigid mechanical brackets and standard fasteners.

- Thermal & Fluid Connections:

  - Gas supply line interface: Standard fittings connecting the gas tank through the gas flow/solenoid valves to the gas heaters/burners.

  - Solar thermal/electrical interface: Secure mounting of solar panels to feed the MPPT charge controller and battery bank.

3. Software & Communication Protocols

- Internal Microcontroller Communication:

  - Inter-device communication (if splitting tasks between Arduino and ESP32) via I2C or UART (serial) protocols.

- Sensor Data Acquisition:

  - Digital data bus for DHT22 temperature and humidity sensors.

  - Analogue-to-Digital Conversion (ADC) for gas leakage and gas flow sensors.

- IoT & Monitoring Data Format:

  - ESP32 utilising Wi-Fi/MQTT or HTTP protocols to transmit real-time telemetry (temperature, humidity, curing stage, and safety alerts) to the user interface or cloud dashboard in standard JSON format.

# 9. Roles & Responsibilities

| Name | Role | Key Responsibilities |
| --- | --- | --- |
| Lynos T Pasi | Project Manager | Coordinate the project, schedule, documentation, integration and final validation. |
| Takudzwa Madoda/ Kelvin T Makacha | Design Lead | Barn structure and thermal design |
| Brighton Njeke/Tashinga E Matarirano | Solar Subsystem Lead | Solar collector/PV sizing and integration |
| Wayne Mukucha/Lynos T. Pasi | Biogas Subsystem Lead | Burner and biogas supply integration |
| Justice Tayengwa/Takura Mupxetedzi | Moisture-harvesting energy subsystem | CAD and electrical testing |
| Thabani J. Chasokela Precious S. Marozva | Testing & Documentation Lead | Instrumentation, data logging, report compilation |

# 10. Sign-Off

| Team Lead | Supervisor | Coordinator |
| --- | --- | --- |
| Signature / Date | Signature / Date | Signature / Date |