# Design Phase: Work Breakdown Structure, Task Assignment and Schedule

Team 10 | Intelligent Hybrid Solar–LPG/Biogas Tobacco Curing Barn | Supervisor: E. Sibanda

Prepared by: Lynos T Pasi (Project Manager) | Version 0.1 DRAFT, 20/10/26 | Design Phase: 20/10/26 to 30/11/26 (Design Review)

## 1. Purpose and how to use this document

This document is the Work Breakdown Structure (WBS) with a Responsibility Assignment Matrix (RACI) and a Gantt-style schedule. It breaks the Design Phase into tasks, names one person responsible for each, lists supporters, sets dates, and defines what each task must produce. It leads to the Design Review on 30/11/26, where the team presents CAD, circuit design and control architecture.

Design goal: a complete, simulated and documented design (SolidWorks mechanical model, Proteus electronics simulation, control firmware design) with an IoT interface for remote monitoring, ready for procurement and build.

Status: All assignments below are PROPOSED. Each person should review their tasks, suggest changes and confirm at the kick-off meeting. Edit this document directly and update the Status column weekly.

Key to roles:

- R = Responsible: does the work and owns the deliverable (one R per task)

- S = Support: works with the owner and shares the workload

- C = Consulted: gives input or reviews before it is finalised

- A = Accountable: the Project Manager (Lynos) is accountable for every deliverable and signs it off

## 2. Team and focus areas

| Member | Charter role | Design-phase focus |
| --- | --- | --- |
| Lynos T Pasi | Project Manager; Biogas/LPG co-lead | Planning, architecture and interfaces, LPG burner and flue layout, design review pack |
| Takudzwa Madoda | Design Lead | Requirements, thermal calculations |
| Kelvin T. Makacha | Design Lead | Chamber CAD, full assembly |
| Brighton Njeke | Solar Subsystem Lead | PV and battery sizing, source switching, ESP32 IoT firmware |
| Tashinga E Matarirano | Solar Subsystem Lead | PV mounting and DC protection, remote dashboard |
| Wayne Mukucha | Biogas/LPG co-lead | LPG safety design, control algorithm |
| Justice Tayengwa | Moisture subsystem, CAD, electrical testing | Condensate capture design, power and actuator circuits |
| Takura Mupxetedzi | Moisture subsystem, CAD, electrical testing | Loading mechanism CAD, Arduino firmware |
| Thabani J. Chasokela | Testing and Documentation Lead | Sensor circuits, Proteus simulation, test plan |
| Precious S. Marozva | Testing and Documentation Lead | Traceability, wiring and layout, documentation |

## 3. Work Breakdown Structure and task list

Dates run in weekly blocks (Tuesday to Monday). Each task is due by the end of its last week.

### WP1: Project management and documentation

| ID | Task | Owner (R) | Support (S) | Start | Due | Deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Kick-off, confirm roles, set up shared drive, version control and file naming | Lynos | Precious | 20/10 | 26/10 | Shared folder structure, confirmed roles |
| 1.2 | Update charter: BOM (flue/heat exchanger, LPG demo setup), moisture subsystem scope, LPG for demonstration | Lynos | Everyone | 20/10 | 02/11 | Charter v2 and updated BOM |
| 1.3 | Weekly meeting, progress tracker, risk log | Lynos | Precious | 20/10 | 30/11 | Weekly minutes, tracker, risk register |
| 1.4 | Design report skeleton and requirements traceability matrix (requirement to design to test) | Precious | Thabani | 27/10 | 30/11 | Report template, traceability matrix |

### WP2: Requirements and system architecture

| ID | Task | Owner (R) | Support (S) | Start | Due | Deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| 2.1 | Curing profile and system requirements: stage temperatures, humidity targets, durations, tolerances, test duration | Takudzwa | Kelvin | 20/10 | 02/11 | Requirements specification |
| 2.2 | System architecture: block diagram, I/O list, pin map, Arduino/ESP32 split, I2C/UART link, MQTT topics, JSON telemetry format | Lynos | Wayne, Brighton, Takura, Thabani | 20/10 | 09/11 | Architecture and interface specification |

### WP3: Mechanical and thermal design (SolidWorks)

| ID | Task | Owner (R) | Support (S) | Start | Due | Deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| 3.1 | Heat load and thermal calculations: insulation, air flow, heater sizing for the 50–70°C stage | Tashinga | Kelvin Thabani Wayne | 27/10 | 16/11 | Thermal calculation sheet |
| 3.2 | Chamber and frame CAD: angle-iron frame, door, insulation, sensor and duct ports, exhaust fan mount | Kelvin | Takudzwa Justin Brighton | 03/11 | 23/11 | Chamber CAD model |
| 3.3 | Tray/rack loading and unloading mechanism CAD: motors, rails or wheels, limit switches | Justin | Kelvin Justin Precious Takura | 27/10 | 23/11 | Mechanism CAD and motion check |
| 3.4 | LPG burner, flue and heat-exchanger layout, with the combustion exhaust vented outside the chamber and duct routing to the chamber | Lynos | Wayne, Takudzwa Brighton | 03/11 | 23/11 | Burner and flue layout |
| 3.5 | Moisture and condensate capture design and one productive use (agricultural or energy-related) | Takudzwa | Precious Lynos kelvin | 03/11 | 23/11 | Condenser design and use-case statement |
| 3.6 | Full SolidWorks assembly, interference check, drawings and exploded views | Kelvin | Takura, Justice, Wayne | 17/11 | 30/11 | Assembly model and drawing pack |

### WP4: Energy subsystems

| ID | Task | Owner (R) | Support (S) | Start | Due | Deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| 4.1 | Energy budget and PV, battery and MPPT sizing for the 12V DC heaters, fans, motors and electronics | Brighton | Tashinga | 27/10 | 09/11 | Sizing calculation |
| 4.2 | PV mounting, 12V DC bus wiring and protection (fuses, MCBs, cable ratings) | Tashinga | Brighton, Justice | 10/11 | 23/11 | DC bus and protection design |
| 4.3 | LPG safety design: regulator, solenoid valve, igniter sequence, flame/leak detection, ventilation, shut-off interlocks | Wayne | Lynos | 27/10 | 16/11 | LPG safety design note |
| 4.4 | Hybrid source-switching strategy: solar only, LPG only, combined; logging of the active source | Brighton | Wayne, Lynos | 03/11 | 16/11 | Switching logic specification |

### WP5: Electronics design and Proteus simulation

| ID | Task | Owner (R) | Support (S) | Start | Due | Deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| 5.1 | Power distribution and protection schematic: 12V bus, 5V and 3.3V regulators, relays or MOSFET drivers, fuses | Justice | Brighton | 03/11 | 16/11 | Power schematic (Proteus) |
| 5.2 | Sensor and instrumentation circuits: DHT22, gas flow, gas leak, ADC, LCD | Thabani | Precious | 27/10 | 16/11 | Sensor schematic (Proteus) |
| 5.3 | Actuator drive circuits: A4988 stepper drivers, heater relays, fan, solenoid valve, igniter | Justice | Takura | 03/11 | 16/11 | Actuator schematic (Proteus) |
| 5.4 | Full-system Proteus simulation of Arduino, sensors and actuators through a curing-stage test sequence | Thabani | Precious, Takura, Wayne | 10/11 | 30/11 | Simulation files and results |
| 5.5 | Wiring diagram, enclosure layout and breadboard/PCB layout, with power and signal wiring separated | Precious | Justice | 17/11 | 30/11 | Wiring diagram and layout |

### WP6: Control firmware and IoT interface

| ID | Task | Owner (R) | Support (S) | Start | Due | Deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| 6.1 | Curing-stage control algorithm: state machine for yellowing, colour fixing and stem drying; hysteresis or PID; safety interlocks and fail-safe states | Wayne | Brighton | 27/10 | 16/11 | State diagram and pseudocode |
| 6.2 | Arduino firmware: sensor reading, heater, fan and valve control, loading mechanism sequence | Takura | Wayne | 10/11 | 30/11 | Firmware (simulated in Proteus) |
| 6.3 | ESP32 IoT firmware: Wi-Fi, MQTT or HTTP, JSON telemetry, abnormality alerts | Brighton | Tashinga | 03/11 | 23/11 | ESP32 firmware and message format |
| 6.4 | Remote dashboard: live temperature and humidity, current curing stage, active energy source, alerts, history, remote setpoints | Tashinga | Precious | 10/11 | 30/11 | Working dashboard prototype |

### WP7: Verification planning and Design Review

| ID | Task | Owner (R) | Support (S) | Start | Due | Deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| 7.1 | Test plan and acceptance criteria mapped to the five success criteria | Thabani | Precious | 10/11 | 23/11 | Test plan |
| 7.2 | Design Review pack and presentation, with an internal dry run and fixes | Lynos | All | 17/11 | 30/11 | Review pack, CAD, circuits, control architecture, updated BOM and risks |

## 4. Responsibility matrix (RACI)

R = Responsible, S = Support, C = Consulted. Lynos is also Accountable (A) for every task as Project Manager.

| ID | Lynos | Takudzwa | Kelvin | Brighton | Tashinga | Wayne | Justice | Takura | Thabani | Precious |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | R |  |  |  |  |  |  |  |  | S |
| 1.2 | R | C | C | C | C | C | C | C | S |  |
| 1.3 | R |  |  |  |  |  |  |  |  | S |
| 1.4 | C |  |  |  |  |  |  |  | S | R |
| 2.1 | C | R | S |  |  |  |  |  |  |  |
| 2.2 | R |  |  | S |  | S |  | S | S |  |
| 3.1 |  | R | S |  |  |  |  |  |  |  |
| 3.2 |  | S | R |  |  |  |  |  |  |  |
| 3.3 |  |  | S |  |  |  |  | R |  |  |
| 3.4 | R | S |  |  |  | S |  |  |  |  |
| 3.5 |  | S |  |  |  |  | R |  |  |  |
| 3.6 | C |  | R |  |  | S | S | S |  |  |
| 4.1 |  |  |  | R | S |  |  |  |  |  |
| 4.2 |  |  |  | S | R |  | S |  |  |  |
| 4.3 | S |  |  |  |  | R |  |  |  |  |
| 4.4 | S |  |  | R |  | S |  |  |  |  |
| 5.1 |  |  |  | S |  |  | R |  |  |  |
| 5.2 |  |  |  |  |  |  |  |  | R | S |
| 5.3 |  |  |  |  |  |  | R | S |  |  |
| 5.4 |  |  |  |  |  | S |  | S | R | S |
| 5.5 |  |  |  |  |  |  | S |  |  | R |
| 6.1 |  |  |  | S |  | R |  |  |  |  |
| 6.2 |  |  |  |  |  | S |  | R |  |  |
| 6.3 |  |  |  | R | S |  |  |  |  |  |
| 6.4 |  |  |  |  | R |  |  |  |  | S |
| 7.1 | C |  |  |  |  |  |  |  | R | S |
| 7.2 | R | S | S | S | S | S | S | S | S | S |

Workload check (number of tasks as R)

## 5. Schedule (Gantt view)

Week 1 = 20–26 Oct, Week 2 = 27 Oct–2 Nov, Week 3 = 3–9 Nov, Week 4 = 10–16 Nov, Week 5 = 17–23 Nov, Week 6 = 24–30 Nov. A filled block (■) means the task is active that week.

| ID | Task (short) | Owner | W1 | W2 | W3 | W4 | W5 | W6 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Kick-off and set-up | Lynos | ■ |  |  |  |  |  |
| 1.2 | Charter and BOM update | Lynos | ■ | ■ |  |  |  |  |
| 1.3 | Weekly meetings and risk log | Lynos | ■ | ■ | ■ | ■ | ■ | ■ |
| 1.4 | Report and traceability | Precious |  | ■ | ■ | ■ | ■ | ■ |
| 2.1 | Requirements spec | Takudzwa | ■ | ■ |  |  |  |  |
| 2.2 | Architecture and interfaces | Lynos | ■ | ■ | ■ |  |  |  |
| 3.1 | Thermal calculations | Tashinga |  | ■ | ■ | ■ |  |  |
| 3.2 | Chamber CAD | Kelvin |  |  | ■ | ■ | ■ |  |
| 3.3 | Loading mechanism CAD | Takura |  | ■ | ■ | ■ | ■ |  |
| 3.4 | LPG burner and flue layout | Lynos |  |  | ■ | ■ | ■ |  |
| 3.5 | Condensate capture design | Takudzwa |  |  | ■ | ■ | ■ |  |
| 3.6 | Full assembly | Kelvin |  |  |  |  | ■ | ■ |
| 4.1 | PV and battery sizing | Brighton |  | ■ | ■ |  |  |  |
| 4.2 | PV mounting and DC protection | Tashinga |  |  |  | ■ | ■ |  |
| 4.3 | LPG safety design | Wayne |  | ■ | ■ | ■ |  |  |
| 4.4 | Source-switching strategy | Brighton |  |  | ■ | ■ |  |  |
| 5.1 | Power schematic | Justice |  |  | ■ | ■ |  |  |
| 5.2 | Sensor circuits | Thabani |  | ■ | ■ | ■ |  |  |
| 5.3 | Actuator circuits | Justice |  |  | ■ | ■ |  |  |
| 5.4 | Proteus full simulation | Thabani |  |  |  | ■ | ■ | ■ |
| 5.5 | Wiring and layout | Precious |  |  |  |  | ■ | ■ |
| 6.1 | Control algorithm | Wayne |  | ■ | ■ | ■ |  |  |
| 6.2 | Arduino firmware | Takura |  |  |  | ■ | ■ | ■ |
| 6.3 | ESP32 IoT firmware | Brighton |  |  | ■ | ■ | ■ |  |
| 6.4 | Remote dashboard | Tashinga |  |  |  | ■ | ■ | ■ |
| 7.1 | Test plan | Thabani |  |  |  | ■ | ■ |  |
| 7.2 | Design Review pack | Lynos |  |  |  |  | ■ | ■ |

## 6. Key dependencies

- 2.1 and 2.2 come first. Thermal, electrical and IoT work all depend on the requirements and the I/O list, so finish them by 02/11 and 09/11.

- 3.1 (heat load) feeds heater sizing in 4.1 and 4.4, and the heater and fan load in 4.1 feeds the power schematic in 5.1.

- 3.4 and 4.3 must be agreed together, because the burner, flue and safety interlocks are one subsystem.

- 2.2 (JSON format and MQTT topics) must be fixed before 6.3 and 6.4 start, so the ESP32 and dashboard teams build against the same message format.

- 5.1 to 5.3 (schematics) must be finished before 5.4 (full simulation). 6.1 (algorithm) must be finished before 6.2 (Arduino firmware).

- 3.2, 3.3, 3.4 and 3.5 must be finished before 3.6 (full assembly). 5.4 and 6.2 must be finished before 7.2.

## 7. IoT interface: minimum requirements for the Design Review

- Live temperature and humidity (two DHT22 sensors), the current curing stage, and the active energy source (solar, LPG or both).

- Alerts for out-of-range temperature or humidity, gas leak, and communication loss.

- History or logging of readings, to support the success criteria for stage temperature control and hybrid energy performance.

- Data sent as JSON over MQTT or HTTP from the ESP32, as stated in the charter's interface contracts.

- Remote setpoint changes (if feasible), with local safety shut-offs that still work if Wi-Fi is lost. The Arduino must fail safe without the cloud.

- A decision on the dashboard platform by 06/11 so that 6.3 and 6.4 are not delayed.

## 8. Design Review deliverables checklist (30/11/26)

- SolidWorks assembly and drawing pack (3.6)

- Proteus schematics and simulation results (5.1 to 5.4)

- Control architecture: block diagram, state machine and IoT data flow (2.2, 6.1, 6.3)

- Thermal, PV and battery calculations (3.1, 4.1)

- LPG safety design and flue layout (3.4, 4.3)

- Updated BOM, risk register and test plan (1.2, 1.3, 7.1)

- Traceability matrix linking requirements, design elements and planned tests (1.4)

## 9. Later phases (indicative, to be confirmed after Design Review)

| Phase | Indicative period | Main activities | Lead |
| --- | --- | --- | --- |
| Procurement | Dec 2026 to Jan 2027 | Finalise BOM, order components, apply Design Review feedback | Lynos, Thabani |
| Subsystem build and bench tests | Jan to Feb 2027 | Build and test solar, LPG/flue, electronics, loading mechanism and IoT separately | Subsystem leads |
| Preliminary Demo | 26/02/27 | Bench-level subsystem demonstration | Tashinga E Matarirano |
| Integration Check | 05/03/27 | Mechanical, electrical and software integrated | Wayne Mukucha, Thabani J. Chasokela |
| Integrated testing and tuning | Mar to Apr 2027 | Run tests against the success criteria and record data | Thabani, Precious |
| Report and poster | Apr 2027 | Final report, poster, documentation closure | Precious, Lynos |
| Final Demo | 30/04/27 | Working prototype, report and poster | Lynos T Pasi, Takura Mupxetedzi |

## 10. Weekly status log

| Week ending | Tasks completed | Tasks at risk or late | Decisions or actions | Updated by |
| --- | --- | --- | --- | --- |
| 26/10 |  |  |  |  |
| 02/11 |  |  |  |  |
| 09/11 |  |  |  |  |
| 16/11 |  |  |  |  |
| 23/11 |  |  |  |  |
| 30/11 |  |  |  |  |